Shashroy Bazar

সাশ্রয় বাজার

Development Plan, Marketing Plan, and Cost & Profit Analysis

Version 1.0

Companion document to the Shashroy Bazar SRS v1.0

All costs are stated in Bangladeshi Taka (BDT). Figures are planning-stage estimates — see Section 4.1 and 4.11.

# Table of Contents

# 1. Introduction

This document builds on the Shashroy Bazar Software Requirements Specification (SRS) v1.0 to present three components needed to move the platform from requirements to a fundable, operating product: (1) a Development Plan covering the full Software Development Life Cycle (SDLC) and project schedule, (2) a Marketing Plan spanning short-term, long-term, and continuous activities, and (3) a Cost and Profit Analysis intended to support an investor pitch. All figures are illustrative planning estimates for a small student/startup team of 5–8 people delivering an MVP in 6–9 months (planned here as 8 months), and are marked as such throughout — consistent with the “pending stakeholder decision” items already flagged in the SRS (D-01 to D-11).

# 2. Development Plan

## 2.1 Development Methodology

Given the team size (5–8 people), evolving business rules (pricing, discount bands, purchase limits — see SRS Section 8), and the need to show working increments to stakeholders and prospective investors, an Agile/Scrum approach with two-week sprints is recommended over a strict Waterfall model. Each SDLC phase below is still performed in full, but requirements, design, and testing are revisited each sprint rather than completed once at the start.

- Sprint length: 2 weeks (≈16–17 sprints across an 8-month build).

- A thin vertical slice (registration → one purchase flow) is targeted by Sprint 4 to de-risk integrations (OTP, eKYC, payment) early.

- A releasable MVP (core FRs from SRS Sections 6.1–6.10) is targeted by the end of Month 7, leaving Month 8 for hardening, security review, and launch preparation.

## 2.2 SDLC Phases and Activities

| SDLC Phase | Key Activities | Primary Deliverables | Duration |
| --- | --- | --- | --- |
| Requirements | Refine SRS v1.0 into sprint-ready user stories; resolve D-01–D-11 decisions with the PM/stakeholders; prioritize backlog | Product backlog, resolved decision log, acceptance criteria per story | Weeks 1–3 (overlaps with Design) |
| Design | System architecture, data model, API contracts, UI/UX wireframes and prototypes, third-party integration design (OTP, eKYC/NID, payment gateways, notifications) | Architecture document, ER diagram, API spec, clickable prototype | Weeks 2–5 |
| Implementation | Sprint-based development of registration/eKYC, zones, merchant/listing, pricing engine, discovery/purchase, donation, delivery, payment, advertising, complaints, admin, notifications | Working, demoable increments each sprint; code merged to main branch with CI checks passing | Weeks 4–28 (Months 2–7) |
| Testing | Unit and integration testing each sprint; end-to-end QA pass per module against SRS acceptance criteria; UAT with a pilot merchant/NGO group; security and payment-flow testing | Test cases mapped to SRS acceptance criteria, defect log, UAT sign-off | Continuous from Week 6; dedicated QA hardening in Month 8 |
| Deployment | Staging environment rollout, production environment setup, phased launch in one pilot zone, app store submission | Deployed staging build, production runbook, pilot-zone go-live | Month 8 |
| Maintenance | Bug fixes, monitoring, incremental feature rollout by zone, quarterly business-rule tuning (discount bands, purchase limits, expiry threshold) | Release notes, monitoring dashboards, quarterly review reports | Month 9 onward (ongoing) |

## 2.3 Project Team Structure

| Role | Count | Primary Responsibility |
| --- | --- | --- |
| Project Manager / Product Owner | 1 | Backlog ownership, stakeholder/PM liaison, sprint planning, scope and decision tracking (D-01–D-11) |
| Backend Developer | 2 | Core services: registration/eKYC, pricing engine, inventory, payment and donation logic, admin/reporting APIs |
| Frontend / Mobile Developer | 2 | Customer, merchant, and admin-facing interfaces; zone-based browsing and checkout flows |
| QA Engineer | 1 | Test-case design against SRS acceptance criteria, regression and UAT coordination, defect management |
| UI/UX Designer (part-time) | 1 (50%) | Wireframes, prototypes, Bangla/English UI content, accessibility review (NFR-16) |

## 2.4 Illustrative Technology Stack

Consistent with the SRS's approach of not prescribing technology, the stack below is illustrative for planning and costing purposes only and remains subject to the development team's feasibility review.

- Backend: a mainstream web framework with REST APIs (e.g., Node.js/Express or Django) and a relational database for transactional integrity (NFR-08, NFR-09).

- Frontend/Mobile: a cross-platform mobile framework (e.g., Flutter or React Native) to cover both smartphone users economically, plus a lightweight admin web console.

- Integrations: SMS/OTP gateway, an approved eKYC/NID verification provider, bKash/Nagad/bank-transfer payment gateways, and a push/SMS notification service.

- Infrastructure: cloud hosting with managed database and backups, in line with NFR-04, NFR-11, and NFR-18.

## 2.5 Project Schedule (8-Month Plan to MVP Launch)

The table below shows each phase's active months (M1–M8). A shaded cell indicates the phase is active in that month.

| Phase | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements | ■ |  |  |  |  |  |  |  |
| Design | ■ | ■ |  |  |  |  |  |  |
| Implementation |  | ■ | ■ | ■ | ■ | ■ | ■ |  |
| Testing / QA |  |  | ■ | ■ | ■ | ■ | ■ | ■ |
| Deployment / Launch Prep |  |  |  |  |  |  | ■ | ■ |
| Pilot-Zone Go-Live |  |  |  |  |  |  |  | ■ |

### Milestones

| Milestone | Target | Exit Criteria |
| --- | --- | --- |
| M1 — Backlog & Architecture Baseline | End of Month 1 | Prioritized backlog; architecture and API contracts approved by PM |
| M2 — Registration/eKYC + Zones Working | End of Month 3 | A user can register, verify via eKYC, and browse zone-filtered listings in staging |
| M3 — End-to-End Purchase Flow | End of Month 5 | A user can browse, buy at a system-calculated price, pay, and select pickup/delivery |
| M4 — Donation, Advertising, Admin Complete | End of Month 7 (MVP feature-complete) | All FR-01–FR-73 modules demoable; UAT begins |
| M5 — Pilot Launch | End of Month 8 | Security review passed; pilot zone live with real merchants and at least one NGO |

## 2.6 Risk Management

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| eKYC/NID verification provider integration delays | Medium | High | Select provider and begin integration in Month 1; keep manual-review fallback (FR-02–FR-04) as a temporary path |
| Payment gateway (bKash/Nagad) commercial approval takes longer than planned (D-08) | Medium | High | Start commercial discussions in parallel with development; design payment module against an abstraction layer so a provider swap doesn't block launch |
| Small team stretched across many modules | Medium | Medium | Strict sprint scoping to MVP-critical FRs; defer FR-59/FR-60 advanced ad-analytics and non-critical admin reports to post-MVP |
| Merchant/NGO adoption slower than expected in pilot zone | Medium | Medium | Recruit pilot merchants and at least one NGO before go-live (see Marketing Plan, Section 3.3) |
| Discount/pricing rule (D-06) unresolved by build time | Low | High | Build the pricing engine as configurable (NFR-12) so the exact 70–80% band can be tuned without a code change |

# 3. Marketing Plan

Shashroy Bazar's marketing plan must build trust in a new category of transaction (discounted surplus food/medicine and donation) while growing three distinct audiences at once: paying customers, verified merchants, and verified NGOs/organizations (the platform's primary revenue source through advertising).

## 3.1 Target Market Segments

| Segment | Description | Primary Motivation |
| --- | --- | --- |
| Price-conscious households and students | Urban residents in the pilot zone looking for steep discounts on safe surplus food/medicine | Save money (70–80% below market price) |
| Merchants (restaurants, groceries, pharmacies, clinics, caterers) | Businesses with recurring unsold or near-expiry stock | Recover some value from stock that would otherwise be discarded; positive brand association |
| NGOs, shelters, and low-income/underprivileged communities | Organizations and individuals who need donated food/medicine | Reliable, verified access to donations |
| Verified NGOs/organizations as advertisers | Organizations wanting visibility for their own campaigns or causes | Reach an engaged, values-aligned user base (this segment funds the platform) |

## 3.2 Positioning and Value Proposition

Position Shashroy Bazar as “the verified, zone-based way to save money and reduce waste — or to give safely.” The tagline (“সাশ্রয়ী দামে, অপচয় কোই” — roughly, “at a saving price, without waste”) should anchor all messaging around three pillars: verified trust (eKYC, merchant verification), real savings (70–80% off), and measurable social impact (donation tracking and impact metrics per FR-70).

## 3.3 Short-Term Marketing Plan (Pre-Launch and Launch, Months 6–9)

Runs alongside the Development Plan's testing/deployment phases (Section 2.5), so the platform has both users and supply on day one.

- Pre-launch waitlist and teaser campaign on Facebook and Instagram (dominant platforms for this audience in Bangladesh), building an email/SMS waitlist ahead of the pilot-zone go-live.

- Recruit 15–20 pilot merchants (restaurants, groceries, pharmacies) in the pilot zone directly, offering the first 1–2 months of listing free of any future merchant-facing charges.

- Onboard at least 2–3 verified NGOs in the pilot zone before launch so the donation flow (SRS Section 6.8) has real recipients from day one.

- University and neighborhood “ambassador” program: student or community volunteers who demo the app in exchange for a small referral incentive.

- Local micro-influencer and community-group outreach (Facebook groups, local WhatsApp/Telegram community channels) rather than expensive celebrity endorsements.

- A modest launch event or press outreach in the pilot zone timed to the SRS Section 2.5 M5 milestone, emphasizing the waste-reduction and donation story for media appeal.

- App Store Optimization (ASO): Bangla + English store listing, screenshots emphasizing savings and verified donation impact.

## 3.4 Long-Term Marketing Plan (6–24 Months Post-Launch)

- Zone-by-zone expansion marketing: replicate the pilot-zone merchant/NGO recruitment playbook in each new service zone as it goes live (paired with SRS FR-08 zone management).

- Formal partnerships with national NGO networks and pharmacy/supermarket chains to onboard merchants at scale rather than one at a time.

- Corporate/CSR partnerships: position advertising packages (SRS Section 6.11) to corporates seeking CSR visibility tied to a concrete, measurable food-waste and donation impact story.

- Referral and loyalty programs once usage data exists: reward both customers and merchants for platform growth and consistent participation.

- Explore co-marketing with mobile financial service providers (bKash/Nagad) once a payment partnership is finalized (D-08), given their large existing user bases.

- Annual “Impact Report” publication (meals saved, donations delivered, waste diverted) as a PR and investor-facing marketing asset, drawing on the reporting module (FR-70).

## 3.5 Continuous / Ongoing Marketing Activities

- Always-on social media calendar: savings highlights, donation success stories, merchant spotlights, and NGO features (2–4 posts/week).

- Push/SMS notifications for time-sensitive listings and personalized re-engagement, built on the existing Notifications module (SRS Section 6.14).

- Ongoing customer support and review monitoring, feeding directly into the Complaints module (Section 6.12) so service issues are resolved quickly and visibly.

- Search engine and app-store optimization maintained on a rolling basis as keywords and competition evolve.

- Quarterly data-driven review of acquisition channels (which channel brings the most verified, active users per Taka spent) to reallocate the continuous marketing budget.

## 3.6 Marketing Channels Summary

| Channel | Primary Use | Phase |
| --- | --- | --- |
| Facebook / Instagram ads and organic content | Awareness, waitlist building, ongoing engagement | Short-term + Continuous |
| Community ambassadors / word-of-mouth | Trust-building in a new pilot zone | Short-term, repeated per new zone (Long-term) |
| Direct merchant/NGO outreach and partnerships | Supply-side and donation-recipient onboarding | Short-term + Long-term |
| App Store / Play Store optimization | Discoverability, conversion from search | Short-term + Continuous |
| Push/SMS notifications | Retention and time-sensitive conversion | Continuous |
| PR / local media / annual impact report | Credibility, investor and NGO-partner visibility | Short-term (launch) + Long-term (annual) |
| Referral and loyalty programs | Retention and low-cost acquisition | Long-term + Continuous |

## 3.7 Marketing KPIs

| KPI | Purpose |
| --- | --- |
| Verified user sign-ups per month, by zone | Tracks demand-side growth against the zone rollout plan |
| Verified merchants and NGOs onboarded per zone | Tracks supply-side and donation-recipient growth |
| Cost per verified, transacting user (by channel) | Guides reallocation of the continuous marketing budget |
| Repeat purchase/donation rate | Measures retention beyond first use |
| Advertising campaigns sold and renewed | Directly tracks the platform's primary revenue driver |
| Donations completed vs. donations submitted | Marketing- and trust-relevant proxy for platform credibility |

# 4. Cost and Profit Analysis

## 4.1 Assumptions and Basis of Estimates

All figures below are planning-stage estimates in BDT, built for a 5–8 person team over an 8-month build (Section 2.5) followed by a pilot-zone launch. They are illustrative — based on typical Bangladeshi early-stage tech-team costs and comparable platform benchmarks — and are not a substitute for a formal costing exercise once the decisions in SRS Section 8 (D-01–D-11) are finalized. Figures should be validated with an accountant or financial advisor before being used in an actual investor pitch or legal fundraising document.

## 4.2 Development (Labor) Cost Breakdown

| Role | Count | Monthly Cost (BDT) | Cost over 8 Months (BDT) |
| --- | --- | --- | --- |
| Project Manager / Product Owner | 1 | 80,000 | 640,000 |
| Backend Developer | 2 | 55,000 each (110,000) | 880,000 |
| Frontend / Mobile Developer | 2 | 50,000 each (100,000) | 800,000 |
| QA Engineer | 1 | 40,000 | 320,000 |
| UI/UX Designer (50%) | 1 | 25,000 | 200,000 |
| Subtotal | 7 | 355,000 / month | 2,840,000 |

## 4.3 One-Time Setup Costs

| Item | Estimated Cost (BDT) |
| --- | --- |
| Company registration and legal setup | 50,000 |
| Branding and logo/UI design assets | 30,000 |
| Google Play Store registration (one-time) | 2,750 |
| Apple App Store registration (annual) | 10,900 |
| eKYC/NID and payment-gateway integration setup fees | 100,000 |
| Pre-launch security review / penetration test | 150,000 |
| Total one-time setup costs | 343,650 |

## 4.4 Infrastructure and Operational Costs

| Item | Monthly Cost — Build Phase (BDT) | Monthly Cost — Post-Launch (BDT) |
| --- | --- | --- |
| Cloud hosting and managed database | 10,000 | 20,000 |
| SMS/OTP gateway | 5,000 | 12,000 |
| eKYC/NID verification API (per-verification, estimated volume) | 5,000 | 15,000 |
| Domain, SSL, third-party dev tools, misc. | 5,000 | 5,000 |
| Payment gateway fees (treated as a platform cost per BR-13) | 0 (pre-revenue) | 8,000 (estimated at pilot volume) |
| Subtotal | 25,000 / month | 60,000 / month |

Build-phase infrastructure cost over 8 months: 25,000 × 8 = 200,000 BDT.

## 4.5 Marketing Cost Breakdown

| Marketing Phase | Components | Estimated Cost (BDT) |
| --- | --- | --- |
| Short-term (pre-launch + launch, ~3 months, Section 3.3) | Social ads (50,000/mo), ambassador incentives (30,000/mo), launch event, PR, ASO | 395,000 total |
| Continuous (post-launch, per month, Section 3.5) | Social media management, partnerships, content, referral incentives, scaling paid ads | 120,000 / month |

Illustrative Year-1 marketing total (3 months short-term + 3 months continuous after launch): 395,000 + (120,000 × 3) = 755,000 BDT.

## 4.6 Total Year 1 Cost Summary

| Cost Category | Estimated Year 1 Total (BDT) |
| --- | --- |
| Development labor (8-month build) | 2,840,000 |
| One-time setup costs | 343,650 |
| Infrastructure — build phase (8 months) | 200,000 |
| Infrastructure/operations — post-launch (4 months) | 240,000 |
| Post-launch maintenance labor (reduced team, 4 months, est. 200,000/mo) | 800,000 |
| Marketing (short-term + partial continuous) | 755,000 |
| Total estimated Year 1 cost | 5,178,650 |

## 4.7 Revenue Model and Year 1 Revenue Projection

Per BR-08/BR-13, customers pay only the product price with no added platform fee, so the primary revenue stream is advertising sold to verified NGOs/organizations (SRS Section 6.11), pending the package/pricing decision at D-10. The projection below is illustrative and assumes a slow post-launch ramp as advertisers are onboarded.

| Post-Launch Month | Active Advertisers | Avg. Package (BDT/mo) | Monthly Ad Revenue (BDT) |
| --- | --- | --- | --- |
| Month 1 (Month 9 overall) | 5 | 5,000 | 25,000 |
| Month 2 (Month 10 overall) | 8 | 5,500 | 44,000 |
| Month 3 (Month 11 overall) | 13 | 5,500 | 71,500 |
| Month 4 (Month 12 overall) | 18 | 6,000 | 108,000 |
| Year 1 total advertising revenue (4 months post-launch) |  |  | 248,500 |

## 4.8 Year 1 Profit & Loss Summary

| Item | Estimated Amount (BDT) |
| --- | --- |
| Total Year 1 revenue (advertising, 4 post-launch months) | 248,500 |
| Total Year 1 cost (Section 4.6) | 5,178,650 |
| Year 1 net result | (4,930,150) — net loss, expected for a pre-profitability Year 1 |

A Year 1 net loss is normal for a two-sided marketplace still building both its user base and its advertiser base; the figure is presented here specifically so investors can size the funding gap it implies.

## 4.9 Break-Even Analysis

At the post-launch run rate in Section 4.4 and 4.5 (infrastructure ~60,000/month + a lean post-MVP team + a reduced ongoing marketing spend, roughly 250,000–300,000 BDT/month in steady state), and assuming advertising revenue continues to grow at a similar pace to Month 9–12 (Section 4.7), advertising revenue would need to reach approximately 275,000 BDT/month to cover steady-state operating cost. At the illustrated growth curve (~25,000 to ~30,000 BDT/month of net new advertiser revenue added per month), break-even is estimated in the range of Month 18–24 from initial launch (i.e., roughly 10–16 months after the Month 9 launch point) — a range, not a committed figure, pending real advertiser conversion data.

## 4.10 Funding Ask and Use of Funds

To carry the project from the current SRS v1.0 stage through Year 1 operations and reach the break-even runway above, an illustrative seed ask is:

| Use of Funds | Amount (BDT) | % of Ask |
| --- | --- | --- |
| Development labor (8-month build) | 2,840,000 | 44% |
| One-time setup costs | 343,650 | 5% |
| Infrastructure (build + Year 1 post-launch) | 440,000 | 7% |
| Post-launch maintenance labor (Year 1 remainder) | 800,000 | 13% |
| Marketing (Year 1) | 755,000 | 12% |
| Contingency buffer (~15%) | 770,000 | 12% |
| Wind-down/runway extension into Year 2 (partial) | 450,000 | 7% |
| Total illustrative seed ask | ~6,400,000 BDT (~64 lakh BDT) | 100% |

## 4.11 Caveats and Disclaimer

- These estimates are planning-stage projections prepared to support internal decision-making and an initial investor conversation. They are not audited financial statements and should not be treated as a guarantee of future results.

- Several inputs remain open per SRS Section 8 (advertising pricing D-10, payment-provider commercial terms D-08, purchase-limit and discount-band decisions D-03/D-06), and each will materially affect real costs and revenue once finalized.

- Before presenting these figures to investors or using them for legal/fundraising purposes, they should be reviewed and validated by a qualified accountant or financial advisor familiar with Bangladeshi market conditions.